## Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#01 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a database to store user's information. Within the database, separate the instructors from the students. Information includes: User ID Password (encrypted) Type of User (Instructor/Student) | 4 | HIGH | HIGH - part of main function of website. |  | 1
#02 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a UI for authentication and registration, same interface for students and instructors. This interface should include a link to registration. The UI should include fields for: User ID Password | 8 | HIGH | HIGH - part of main function of website. |  | 1
#03 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Test the authentication using the interface and database. Test is successful if: 1- User successfully logs in if credentials are right 2- User cannot log in if credentials are wrong. 3- The UI alerts the user that the username or password is wrong. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#04 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create a function for user registration, taking the information from the user input on the UI. The new used should be permanently saved in the database. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#05 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create a UI for registration. The user should input: 1- Unique User ID 2- Unique Password 3- Email 4- Needs to specify if student or instructor. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#06 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create limitations to the registration such that it is efficient and does not confuse the whole application (many duplicated, not a real instructor etc.) | 8 | HIGH | HIGH - part of main function of website. |  | 1
#02 | US#02: As an instructor, I want to log into the system using my university credentials so that I can manage teams and view assessments. | - Instructors can log in using their university email and password. - Successful login redirects to the instructor dashboard. - Unsuccessful login shows an error message. Associated tasks: TASK#01, TASK#02 and TASK#03 | 5 | HIGH | HIGH - part of main function of website. |  | 1
#04 | US#04: As an instructor, I want to import a course roster from a CSV file to set up teams. | - Instructors can upload a CSV file containing student information. - The system parses the CSV and creates student accounts and teams accordingly. - Errors in the CSV file are reported back to the instructor. Associated tasks: TASK#12 and TASK#13 | 8 | MEDIUM | MEDIUM - not essential for the program to run but it is still a requirement |  | 1
#05 | US#05: As a student, I want to see the team I am assigned to so that I know who my teammates are. | - Students can view their team members on their dashboard. - Team information is updated in real-time. Associated tasks: TASK#15 | 5 | HIGH | HIGH - part of main function of website. |  | 1
#04 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a function for user registration, taking the information from the user input on the UI. The new used should be permanently saved in the database. | 8 | HIGH |  |  | 1
#05 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a UI for registration. The user should input: 1- Unique User ID 2- Unique Password 3- Email 4- Needs to specify if student or instructor. | 8 | HIGH |  |  | 1
#08 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | The database should have a section for teams. It should not create duplicate of each student to save server space, but link them to a team. It should be able to take the instruction from the UI | 8 | HIGH | HIGH - part of main function of website. |  | 1
#09 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | Instructors can create new teams and enroll students from a list. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#10 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | A successful test is where the instructor is able to create a team, to be saved in the database and then be shown in the student and instructor dashboard. | 8 | HIGH | HIGH - Fucntionality testing |  | 1

## US1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#01 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a database to store user's information. Within the database, separate the instructors from the students. Information includes: User ID Password (encrypted) Type of User (Instructor/Student) | 4 | HIGH | HIGH - part of main function of website. |  | 1
#02 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a UI for authentication and registration, same interface for students and instructors. This interface should include a link to registration. The UI should include fields for: User ID Password | 8 | HIGH | HIGH - part of main function of website. |  | 1
#03 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Test the authentication using the interface and database. Test is successful if: 1- User successfully logs in if credentials are right 2- User cannot log in if credentials are wrong. 3- The UI alerts the user that the username or password is wrong. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#04 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create a function for user registration, taking the information from the user input on the UI. The new used should be permanently saved in the database. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#05 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create a UI for registration. The user should input: 1- Unique User ID 2- Unique Password 3- Email 4- Needs to specify if student or instructor. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#06 | #06 As a student, I want to be able to register in the website using my full name, a username, ID and password | Create limitations to the registration such that it is efficient and does not confuse the whole application (many duplicated, not a real instructor etc.) | 8 | HIGH | HIGH - part of main function of website. |  | 1
#07
#08
#09
#10
#11
#12
#13

## US3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#08 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | The database should have a section for teams. It should not create duplicate of each student to save server space, but link them to a team. It should be able to take the instruction from the UI | 8 | HIGH | HIGH - part of main function of website. |  | 1
#09 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | Instructors can create new teams and enroll students from a list. | 8 | HIGH | HIGH - part of main function of website. |  | 1
#10 | #03: As an instructor, I want to create teams and assign students so that I can organize the project teams. Instructors can create new teams. Instructors can assign students to teams. Teams and their members are visible on the instructor dashboard. | A successful test is where the instructor is able to create a team, to be saved in the database and then be shown in the student and instructor dashboard. | 8 | HIGH | HIGH - Fucntionality testing |  | 1
#11
#12
#13
#14
#15
#16
#17
#18
#19
#20

## US2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#02 | US#02: As an instructor, I want to log into the system using my university credentials so that I can manage teams and view assessments. | - Instructors can log in using their university email and password. - Successful login redirects to the instructor dashboard. - Unsuccessful login shows an error message. Associated tasks: TASK#01, TASK#02 and TASK#03 | 5 - Completing this would mean having the databse be separated into students and instructors. Only after this can we separate the dashboards into two different ones. | HIGH | HIGH - part of main function of website. |  | 1
#04 | US#04: As an instructor, I want to import a course roster from a CSV file to set up teams. | - Instructors can upload a CSV file containing student information. - The system parses the CSV and creates student accounts and teams accordingly. - Errors in the CSV file are reported back to the instructor. Associated tasks: TASK#12 and TASK#13 | 8 - Completing this would mean the program would have to read an uploaded file and check if the data corresponds to the data in the database and it should also be able to add this new data to the database. | MEDIUM | MEDIUM - not essential for the program to run but it is still a requirement |  | 1
#05 | US#05: As a student, I want to see the team I am assigned to so that I know who my teammates are. | - Students can view their team members on their dashboard. - Team information is updated in real-time. Associated tasks: TASK#15 | 5 - Completing this would mean the student is able to see their associated team from the database displayed to the dashboard. Only after this is done can the student dashboard be completed. | HIGH | HIGH - part of main function of website. |  | 1
#04 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a function for user registration, taking the information from the user input on the UI. The new used should be permanently saved in the database. | 8 - Completing this would mean having the free time table created as well as the matching algorithm. Only after this can the controller display the necessary data. | HIGH
#05 | #01 As a student, I want to log into the system using my university credentials so that I can access my team and evaluation tasks. | Create a UI for registration. The user should input: 1- Unique User ID 2- Unique Password 3- Email 4- Needs to specify if student or instructor. | 8 - Completing this would mean having the free time table created as well as the matching algorithm. Only after this can the controller display the necessary data.
#06 | [6 empty] | 1
#07 | [6 empty] | 1
#08 | [6 empty] | 1
#09 | [6 empty] | 1
#10 | [6 empty] | 1
#11 | [6 empty] | 1
#12 | [6 empty] | 1
#13 | [6 empty] | 1